## Communications and Technology
Area | Assigned To | Status | Possible Start Date | Possible End Date | Action
Commincation and Technology
Parish-Wide Communication
Identify parishioners’ preference for receiving information about the church by surveying parishioners.
Review current website, calendar and data base system to find the most effective way of evangelizing our faith to our parishioners. Create a permanent technology committee. Take steps to determine our technology needs.
Provide Christmas and Easter Cards to all attendees of Christmas and Easter services.
Create a mechanism to allow parishioners to bring things to our attention. Consider different ways to gather feedback.
Increase awareness and understanding of various councils, commissions, committees and other volunteer/serving opportunities as well as parishioner programs. Create a comprehensive directory of all councils, commissions and committees in the parish.
Provide options for new parishioners and volunteers to register/sign up. Look at ways to make this easier
Provide more opportunities for the parish to come together and develop more effective communication about events and opportunities.
Internal Communication
Increase communication between various councils, commissions and committees by posting notes on the website.
Bi-Lingual Communication
Provide clear and consistent bi-lingual communication to support ecclesial integration

## Engaged Church
Area | Assigned To | Status | Possible Start Date | Possible End Date | Action
Engaged Church
Volunteers
Engage parishioners more by creating a list for all volunteer opportunities and developing a database to match opportunities to volunteers based on their talents.
Staff all tables at the ministry fair and give the time and talent cards directly to the Stewardship Commission.
Establish a volunteer coordinator position.
Current Parishioners
Identify and develop different activities that celebrate the diversity of our parish, including ways that allow full participation from the community. Use Archdiocesan resources.
Continue to develop a welcoming atmosphere for all who attend St. Brendan by encouraging introductions before Mass, train greeters to warmly welcome all who come to St. Brendan, and personally invite parish members to participate and engage in our community.
New Parishioners
Welcome and incorporate new parishioners into the parish by having the Pastor acknowledge them at Mass.
Review the current welcome packet and see if any changes should be made.
After new members attend a Newcomer Social, follow up and check in with them.
Assign an existing family to “adopt” a new family.
Specialized Activities
Provide opportunities for parishioners to come together for fellowship and form relationships and stronger bonds as a Church family by organizing events after Mass.
Identify needs within the parish and facilitate formation of social groups as necessary.
Organize social events for parishioners.

## Facilities
Area | Assigned To | Status | Possible Start Date | Possible End Date | Action
Facilities
Maintenance of Facilities
Provide adequate maintenance and timely upkeep of the Church grounds by clearing the snow and improving the maintenance of outdoor areas.
Maintain cleanliness of indoor Church facilities by recruiting and training volunteers for weekend Masses.
Upgrade Facilities
Upgrade the accessibility of all facilities, including the restrooms and parking areas, with adequate lighting and signage to allow easy and safe access for persons with disabilities.
Reconfigure the restrooms so that they are more accessible.
Improve the sound system in the Nave to encourage better and fuller participation. Evaluate and implement systems that will improve areas with poor sound.
Evaluate and improve the hearing impaired audio equipment.
Provide increased access to the Church/Chapel during off hours. Devise a secure way to allow parishioners more access.
Improve lighting in Nave for fuller participation and safety of the assembly.
Explore options to increase parking spaces, especially during major events.
Expand Facilities
Evaluate methods to allow parishioners to view the meeting space calendar in order to improve access to meeting spaces for programs and activities
Develop a plan for a Parish Center as a long term goal to allow for growth in the Parish and in parish activities and programs

## Faith Formation
Area | Assigned To | Status | Possible Start Date | Possible End Date | Action
Faith Formation
Parish-Wide Faith Formation Survey
Assess the catechetical programs of our parish by using a variety of methods, including the Archdiocesan Faith Formation Assessment and other surveys.
Parish Evangelization
Provide opportunities for the parish to be evangelized through having a deeper encounter with Jesus Christ.
Provide more retreats including Spanish language retreats.
Review the recommended evangelization programs to determine the best fit for our parish.
Families and Young Children (Up to Grade 5)
Evaluate, select and implement successful programs that serve preschool through 5th grade by reviewing and comparing publications that meet faith formation guidelines for the Archdiocese.
Train catechists and other volunteers for family catechesis programs and adapt faith formation programs which involve parents/guardians at all levels.
Provide childcare for families with small children.
Inter-generational Family Catechesis
Consider adoption of an inter-generational catechetical model for families and children for all levels of family faith formation.
LifeTeen
Provide opportunities for regular Eucharist-based youth involvement in liturgy and music using the “LifeTeen Program,” as a tool that enhances the growth of their faith and engagement with the parish.
Begin by identifying and empowering a Youth Music Minister to develop the music ministry for this program. Identify, train and schedule lay people to expose and repose the Eucharist.
Celebrate weekly LifeTeen Mass once we have active participation in LifeTeen activities along with demonstrated parental involvement.
Celebrate bilingual youth Mass once every month when youth Mass is more than once a month and there is demonstrated Hispanic teen participation and parental involvement.
Encourage teens to serve their community by offering opportunities to volunteer within and outside the parish.
Build LifeTeen core team volunteers by continuing to recruit LifeTeen core team members and provide training for them. Encourage attendance at LifeTeen/Edge trainings/conferences and provide funding for participants.
Edge
Continue to provide Youth Retreats to middle-school/junior high aged students using the LifeTeen/Edge curriculum.
Promote youth ministry by encouraging youth to participate in the liturgy. Youth could volunteer in liturgies as part of their service hours.
Young Adult
Create a faith program for young adults of the parish and begin by tapping into deanery-wide young adult programs.
Assess UW Newman Center program as a potential model for the possibility of St. Brendan becoming a “Newman Center” for UW Bothell.
Quinceañera
Strengthen our Quinceañera program through using the Archdiocesan Quinceañera guidelines.
Educate our parish on the cultural importance of the Quinceañera.

## Life, Peace, and Justice
Area | Assigned To | Status | Possible Start Date | Possible End Date | Action
Life, Peace and Justice
Living out our Christian Values
Increase opportunities for working with the homeless.
Survey the parish regarding support for a cold weather overflow shelter. Work with other local churches to gather support and gather volunteers to staff a cold weather overflow shelter
Make known other Life, Peace and Justice opportunities.
Arrange for speakers to discuss social justice issues.
Encourage small adult teams to tackle issues of social injustice and recommend how the parish can help.

## Liturgy
Area | Assigned To | Status | Possible Start Date | Possible End Date | Action
Liturgy
Liturgical Ministry
Increase the understanding of the liturgy of the Mass, the importance of community and make Mass a more spiritual experience. Provide annual training for liturgical ministers on the logistical and theological aspects of their tasks.
Music
Enhance participation during Mass through liturgical music.
Fund attendance for choir members at workshops about vocal, instrumental and liturgical music.
Childcare
Increase engagement of parents during Mass by offering childcare during all Masses and provide other options for parents to listen to Mass if they chose not to use childcare.
Cross Cultural Activities
More fully integrate and celebrate the diversity of our parish by working with our communities to understand how to best incorporate cultural celebrations.

## School
Area | Assigned To | Status | Possible Start Date | Possible End Date | Action
School
School/Church Relationship
Continue to enhance the parish and school relationship by communicating a wide variety of school and parish events and news, highlighting various accomplishments, planning shared events, and working collaboratively with the staff and committees from the parish and school.
Identify and implement additional vehicles of communication between the school and parish, such as more use of kiosks, website calendar, bulletin inserts, information in the narthex, parent speakers and videos at weekend Masses, school and parish website, etc.
Further develop parish based opportunities for volunteer hours for parish and school students and parents to increase parish involvement.
Build relationships between the parish youth and school students through the Parish Youth Group and shared activities.
Provide opportunities for parish and school youth and seniors to interact, work in service, and share time together.
Accessibility
Share school registration information and the tuition assistance process with the entire parish community.
Provide school registration, news/bulletins, and tuition assistance information in Spanish and market to Hispanic parishioners with children.
Offer school tours in both English and Spanish.
Continue to share tuition costs as compared to other local Catholic schools. Show St. Brendan School as being the most affordable on the Eastside. Communicate using a variety of methods.
Finance
Continue to develop, educate, and enhance school donation opportunities for parishioners and organizations by sharing the various options to donate.
Develop a plan to ask parishioner families to financially sponsor a student in need of tuition assistance.
Continue to share the school’s annual financial report with the parish at large, Parish Finance Council, and Pastoral Council.
Create a school five-year financial plan to address the school’s future needs for staffing, technology, curriculum, and plan for additional tuition assistance for families in need.
Create a five-year school major maintenance and repair facilities plan to address the safety, repair, maintenance expansion, and improvement of the school campus. Present the plan to the Parish Facilities Committee, Pastoral Council, and Parish Finance Council for review and funding approval.